## Sheet1
Deliverables | Estimated Time | Actual | Date Expected | Date Completed
Write Assembly code | 1 | 4 | 2014-11-21 | 2014-11-26
Write up for assembly | 0.5 | 0.5 | 2014-11-21 | 2014-11-30
Description and Diagram | 0.75 | 1 | 2014-12-01 | 2014-11-30
Processor Components | 2 |  | 2014-12-02
Components Test Benches | 2 |  | 2014-12-02
Combining Components | 2 |  | 2014-12-03
Test Strategy Explanation | 1 |  | 2014-12-03
Polish/Finish the Writeup | 2 |  | 2014-12-04
Total: | 11.25
We've set a couple of preliminary meeting times for before and during break. These times are overestimates, but we feel that is safer than underestimating.